## Master Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions.
|  |  | Last updated: |  | 2024-07-01
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  |  | Program Start: |  | 2024-07-01
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Integration Project Schedule |  | Display Week: |  | 1 |  |  | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05 | [6 empty] | 2024-08-12 | [6 empty] | 2024-08-19 | [6 empty] | 2024-08-26 | [6 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2024-07-01 to 2025-01-05
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | RESPONSIBLE LEAD | PROGRESS | DURATION | START | END | DAYS | time axis 2024-07-01 to 2025-01-05
| NHSD Integration |  |  |  | x | x
| Example task (line to be deleted) | HDA | 75% | 1 | 2022-02-07 | 2022-02-08
| NHSD Agreement executed | HDA & Integrator |  | 0
| Kickoff meeting - introduction to the onboarding pack | HDA & Integrator |  | 1
Data Harmonisation
| Meeting: review of data definitions | HDA & Integrator |  | 1
| Confirm data attributes to be harmonised | HDA & Integrator |  | 5
| Data harmonisation | HDA |  | 30
| Variance reporting | HDA |  | 5
| Implementation of recommendations until data is harmonised | Integrator |  | ?
| Updates made to DSA if required | HDA & Integrator |  | 5
Build activities
| API Specification review meeting (optional) | HDA & Integrator |  | 1
| API build | Integrator |  | ?
| ? | Integrator |  | ?
| ? | Integrator |  | ?
| Vendor submits NHSD connection request | Integrator |  | 1
Testing
| Submit test environment access request | Integrator |  | 1
| Data provider credentials created/IP whitelisted | HDA |  | 1
| Provision of API key, client credentials and test scenarios | HDA |  | 1
| Data provider conducts in-house integration testing & provides Healthdirect with a Test Summary | Integrator |  | ?
| Request to complete NOC, providing completed excel test scnario spreadsheet. | Integrator |  | 1
| NHSD team conducts integration testing | HDA |  | 5
| NHSD verifies results and finalises the Notice of Connection (NOC) | HDA |  | 1
Release management
| On Successsful completion of testing, PROD client credentials and API key provided | HDA |  | 1
| Integrator to connect API to PROD Data Aquisition Hub | Integrator |  | 1
| Meeting: conformance demo of final product | HDA & Integrator |  | 1
| NOC provided | HDA |  | 1
Formulas:
x = IF([x]="","",[x]+E9)
Note on F3: Example only - begin by inputting a date.
Note on B4: Note: This schedule can be copy/pasted into MS Project, if your organisation uses that software.
Note on D6: Input percentages, 1-100
Note on E6: Duration in Days
Note on B23: API Build is responsibility of the vendor - this section is left blank for the vendor to input tasks aligning with their preferrred project management methodology.

## Queries & Actions register
ACTION TRACKER - NHSD Integration Project
Ref | WORKSTREAM | Date raised | Action | Owner | Updates/Progress | Status (open/closed) | Answer date
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18